## Slide 1: Commercial Tin
June 11, 2012
Angela Y.
Oncotype DX Patient

## Slide 2: Commercial Tin
Goal:
To provide a generalized WCF (Windows Communication
Foundation) service to interact with our current shipping
source, FedEx.
  This will allow us to change interfaces or even companies without having to release upgrades to our major components.

## Slide 3: Commercial Tin
Objectives:
GHI/FedEx integration upgrade:
  Upgrade to the latest version of the FedEx API (v10). The version of the FedEx API we used before Tin will expire on May 2012.
  Re-design of our shipping code for increased flexibility.
Microsoft .NET framework upgrade to 4.0 (RDS and ShipService)

## Slide 4: Commercial Tin
Commercial Tin (RDS 2.7.0/ShipService 1.0.0/.NET 4.0)
Milestones:
  Hand-off 1: 02/07/2012 - 02/23/2012 (Nunit development and execution)
  Hand-off 2: 02/24/2012 – 02/07/2012 (Active testing: functional, regression, connectivity, print and live testing)

## Slide 5: Commercial Tin
Tester’s Name | Apps Tested | Test Activities
Charul Goel | Commercial Tin | Functional, regression, live testing, Nunit development, QASource support, SRS fix verification.
Vandana Mathur | Commercial Tin | Print, connectivity testing.
Shilpa Sharma | Commercial Tin | Functional and regression testing, SRS fix verification.
Sheetal Sharma | Commercial Tin | Functional and regression testing, SRS fix verification.
Sweety Sharma | Commercial Tin | Functional and regression testing, SRS fix verification

## Slide 6: Commercial Tin
Bugs:
  Found:21
  Fixed/ Verified:21
  Cancelled: 3
Test case execution:
  Test Cases planned: 68
  Test Cases executed:68
  Passed Test Cases: 68
  Failed Test Cases: 0
Release date:
  03/10/2012 (Originally planned)
  04/03/2012 (Re-deployment)

## Slide 7: Commercial Tin – Redeployment
Post-Deployment Problem observation
  A delay in generating waybills due to Tin release (integration with the latest FedEx shipping API).
  What took 3 seconds for printing (using images) previously, now start taking 30 seconds for printing (using PDFs), while delaying other operations that are sequentially queued.

## Slide 8: Commercial Tin – Redeployment
Problem explanation:
  The increased time to print a PDF waybill was known at the time of development and deployment.
  The staff in clinical materials was also made aware of this difference.
  Unfortunately, when looking at just one or two shipments at a time, the amount of time to print a PDF waybill seems well within the acceptable limit.
  When we multiply that increase by several hundred shipments, however, the impact on the print and shipping queue becomes severe

## Slide 9: Commercial Tin – Redeployment
Solution:
  Near term (Tin)
  Rolling back to use image format for waybills.
  Long term (Nitrogen)
  Introduction of task parallelization, when report printing will be
  separated from the rest of print activities by implementing two
  RDS instances located on two different machines.
  Introduction of the requirement focusing on “batch printing”,
  specifying batch size and the expected time in between when
  the batch is kicked off and the reports are on the printer.

## Slide 10: Commercial Tin – Redeployment
Lessons learned
  The performance test task was assigned to development team due to lack of QA time because of the large number of SRSs introduced and some other issues.
  Development team did conduct performance testing around the FedEx ship service itself to insure that the new calls to FedEx would not be a bottleneck.
  Development team did not do the same type of testing around the waybill printing itself.
  Neither related requirement, nor benchmark data has been included in ERD, and, as a result, this use case has not be considered during both, testing and UAT.